## Munka1
Type | ID | Variable name | Short description (what it measures) | Why is it important to measure in an activity-on-node project network?
Time | XDUR | average activity duration | Sum of activity durations divided by the number of activities. | Shows the average units of the durations in projects.
Time | VADUR | variance in activity durations | Variance in the duration of activities. | Likely to have an effect on scheduling on the basis of activity duration.
Time | MAXCPL | maximum critical path length | Total project time or the longest critical path length. | The minimal duration of the project / portfolio considering the earliest (resource-unconstrained) start schedule.
Time | NSLACK | number of activities with positive (nonzero) total float | Counts total number of nonzero activity float(s) | Reflects scheduling freedom in the sense that specific activities can be delayed without delaying the completion of a project.
Time | PCTSLACK | percentage of activities with positive (nonzero) total float | The ratio of nonzero activity float(s) and all activities. | Reflects scheduling freedom in the sense that specific activities can be delayed without delaying the completion of a project.
Time | TOTSLACK_R | total slack ratio | Total slack (float) of all activities divided by the critical path length. | Reflects scheduling freedom in the sense that specific activities can be delayed without delaying the completion of a project.
Time | XSLACK | average slack | Average total slack per activity | Reflects scheduling freedom in the sense that specific activities can be delayed without delaying the completion of a project.
Time | XSLACK_R | average slack ratio | Average slack ratio on the critical path | Reflects scheduling freedom in the sense that specific activities can be delayed without delaying the completion of a project.
Time | NFREESLK | number of activities with positive (nonzero) free slack | Counts total number of nonzero activity slack(s) | Reflects scheduling freedom of specific activities can be delayed without delaying any other starts of the activities in the project.
Time | PCTFREESLK | percentage of activities with positive (nonzero) free slack | The ratio of nonzero activity slack(s) and all activities | Reflects scheduling freedom of specific activities can be delayed without delaying any other starts of the activities in the project.
Time | XFREESLK | average free slack | Average free slack per activity | Reflects scheduling freedom of specific activities can be delayed without delaying any other starts of the activities in the project.
Resource | NRES | number of renewable resources | How many resources are available for scheduling activities. | Number of renewable resources in the project.
Resource | XDMND | average resource demand | Average quantity of resources demanded if required by an activity. | Shows the average units of the resources in projects.
Resource | RU | resource use | Measures for each activity the number of resource types used. | How tasks are using resources types. Is a vector of the number of different resources each activity uses.
Resource | XUTIL | average resource utilization | The average utilization of resource types on the longest critical path length. | Assessing resource efficiency and identifying resource bottlenecks.
Resource | PCTR | percentage of activities requiring positive amount of resource type | Percentage of activities that require the given resource type | How resources are distributed among activities.
Resource | RS | resource strength | Measures the availability of resources (normalized) for the earliest start schedule. | Assessing the resource feasibility and identifying the resource gaps for the earliest start schedule.
Resource | A_RS | alpha distribution of resource strength | Measures the variation (α-distance) of multiple resource strength indicators. | Shows the variation of resource strengths in unconnected (sub)prujects.
Resource | NARLF | normalized average resource loading factor | Shows whether the resource demands for all projects with the earliest start schedule occur in the first or second half of the critical path duration of the portfolio. | To know whether resource demand is front- or backloaded in the project (portfolio).
Resource | GINI | Gini coefficient | How the total work content (each activity’s renewable resource demand multiplied by its duration) is distributed among all activities. | (In)equality of renewable resource profiles among tasks.
Resource | RC | resource constrainedness (for each resource type) | Measures per resource type the average quantity demanded by all activities divided by its availability. | Considers the amount of the resource needed.
Resource | XCON | average resource constrainedness over time | Sum of renewable resource demands (divided by the number of non-zero demands) divided by the availability of the given resource type. | Reflects the "tightness" of certain resource types.
Resource | RF | resource factor | Average portion of resource types requested per activity. | Density of the resource matrix. Does not account for the amount of the resource needs.
Resource | TOTOFACT | total obstruction factor | Excess resource requirements divided by resource work content (duration multiplied by resource demand), measured for the earliest start schedule. | Excessive resource needs.
Resource | TOTUFACT | total underutilization factor | Total resources need less than available divided by work content (duration multiplied by resource demand) for the earliest start schedule. | Reflects underutilization (demand below availability) of resources.
Logic | TASKS | number of activities | Measures the size of the network as the number of activities. | How many activities are present in the project (portfolio).
Logic | I2 | serial-parallel (SP) | Measures the closeness to series or parallel graph. | Determines the number of serial activities in the network on the longest chain.
Logic | I3 | activity distribution (AD) | Measures the distribution of the activities over the progressive levels on the basis of the width of each progressive level in the network. | Measures how the project activities that do not belong to the longest chain are distributed in the network.
Logic | I4 | the length of long arcs (LA) | Measures the presence of long precedence relations. The length of an arc is the difference between the progressive level of the end node and the start node. | A lower value indicates many dependencies between two levels of activities; a higher value indicates the presence of many immediate successors at the next level of the network.
Logic | I5 | short arcs (SA) | Measures the presence of short precedence relations. The length of an arc is the difference between the progressive level of the end node and the start node. | Alternative for I4 (length of long arcs).
Logic | I6 | topological float (TF) | Ont the basis of the difference between the progressive and regressive levels of each activity, the topological float indicator is defined as the fractional total topological float in relation to its maximum. | The topological float of a precedence relation is the number of levels that each activity can shift without violating the maximal level of the network.
Logic | C | network complexity | The average number of non-redundant arcs per node. | The number of redundant arcs should not have an influence on project complexity.
Logic | CNC | coefficient of network complexity | A measure of the connectedness of a graph takes redundant nodes into account. | A higher complexity means greater connectedness of the network. However, many network problems become easier with increasing CNC.
Logic | OS | order strength | The number of precedence relations (including the transitive ones) divided by the theoretical maximum number of precedence relations. | Assessing the complexity and flexibility of the project network and the project schedule.
Logic | TDENSITY | total activity density | Measure the interconnectedness of a network. The sum of the maximal number of predecessors minus successors of each activity. | Influences when (in terms of network logic) an activity can be scheduled
Logic | XDENSITY | average activity density | Sum of the maximal number of predecessors minus successors of each activity, divided by the number of activities | Influences when (in terms of network logic) an activity can be scheduled
Logic | AP | number of articulation points | The number of tasks (and their dependencies) to remove to disconnect the graph (cut vertices). | Removing of articulation points increases the number of connected components in a graph.
Logic | COMPS | components | Size of the largest (strongly) connected component. | The robustness of the network against disruptions.
Logic | MEAN_DEGREE | degrees | The average number of dependencies connected to each task. | The average degree of each task.
Logic | NARC | number of arcs | Number of arcs (precedence relationships). | How many dependencies each task have.
Network | Dens | density | How many dependencies exist in the project network | Degree of complexity of the project network
Network | Diam | diameter | The longest shortest distance between any pair of tasks in the project network. | The degree of dispersion or concentration of the project network.
Network | AVPL | average path length | Average shortest distance between any pair of tasks in the project network | The degree of dispersion or concentration of the project network.
Network | VAs | vertex asymmetries | How asymmetric the network is in terms of the distribution of dependencies among the tasks. | The degree of inequality or diversity in the network structure.
Network | Mot | number of motifs | The number of recurring patterns of dependencies in the project network. | The degree of regularity or randomness of the network.
Network | ASSORT | assortativity | How similar the nodes are in terms of their degree; the degree is the number of connections they have. | Revealing the degree of homogeneity or heterogeneity in the project network structure
Network | LeM | Leiden's graph modularity value | How well the network can be partitioned into communities. | Degree of diversity or cohesion in the project network.
Network | IM | Infomap's graph modularity value | How well the network can be partitioned into communities. | Degree of diversity or cohesion in the project network.
Network | SGM | Spin-Glass graph modularity value | How well the network can be partitioned into communities. | Degree of diversity or cohesion in the project network.
Network | DZI | in-degree centralization | How concentrated the dependencies are on a few activities | The degree of dependency that some activities have over others.
Network | DZO | out-degree centralization | How concentrated the dependencies are on a few activities | Degree of influence that some activities have over others.
Network | DZ | degree centralization | How concentrated the dependencies are on a few activities | Degree of dependency and influence that some activities have over others.
Network | CZ | closeness centralization | How close a task is to all other tasks in the network, on the basis of the sum of the shortest distances between them. | Degree of accessibility or reachability that some tasks have in the network.
Network | HZ | harmonic centralization | How close a task is to all other tasks in the network, which is on the basis of the harmonic mean of the distances between them. | The degree of efficiency or effectiveness that some tasks have in the project network.
Network | EZ | eigenvector centralization | How connected a task is to other well-connected tasks in the network, on the basis of the eigenvector of the adjacency matrix. | Degree of importance that some tasks have in the project network
Network | PRZ | PageRank centralization | How influential or critical a task is for overall project performance. | The degree of impact that some tasks have on the project network.
Network | AZ | alpha centralization | This measures how centralized the network is as a whole, on the basis of the alpha index. | Degree of hierarchy or equality in the project network structure.
Network | PZ | power centralization | This measures how centralized the network is as a whole on the basis of the power index. | Degree of dominance or balance in the project network structure.
Network | BZ | betweenness centralization | How often a task lies on the shortest path between two other tasks. | Degree of intermediation that some tasks have in the project network.
Network | BEZ | edge-betweenness centralization | How often an edge lies on the shortest path between two tasks | The degree of vulnerability or robustness of the project network.
Network | RRes | resilience for random attack | How well the network can maintain its connectivity when a fraction of tasks are randomly removed. | Degree of robustness or susceptibility of the network.
Network | SRes | resilience for systematic attack | How well the network can maintain connectivity when a fraction of (high-degree) tasks are systematically removed. | Degree of robustness or susceptibility of the network.
Network | ALE | average local efficiency | Average efficiency of the subgraphs induced by the dependencies of each task in the project network. | Degree of redundancy or fragility of the project network.
Network | GE | global efficiency | Average efficiency of the network as a whole. | Degree of redundancy or fragility of the project network.
Network | Tra | graph transitivity | Ratio of ratio of triangles to triplets in an project network. | Degree of cliquishness or openness of the project network.